## Slide 1
Workpackage 3 - Train the trainers course in Rome (IT) for health and sport professionals and dance teachers/therapists and national replications of the course (M2 – M12)
WP Leader: Università degli Studi di Roma Foro Italico (IT)
A EU collaborative partnership for active lifestyles for the prevention and treatment of breast cancer
DANCING WITH HEALTH

## Slide 2
Time schedule of WP3
M2-M3: launch the selection process and selection of participants and trainers
M4: Definition of the training contents
M5 – M7: Organization of the course in Italy
M8 – M11: Replication of the course in the participating countries
M12: Follow up of the courses

## Slide 3
Train the Trainers Course
Rome, 8-10 June 2018
For exercise professionals and dance teachers working in the selected countries
For each country:
1 exercise & health professional
2 dance teachers/trainers
Replication of the course in their country

## Slide 4
Train the Trainers Course:
Selection of participants
2 Professional Dancers
- Experienced dancers
Age: 24-60 years
With at least 5 years of experience
1 Exercise professional
Degree in Sport and Movement Sciences
Experience in dance

## Slide 5
Train the Trainers Course:
Selection of participants
The partners will have to select the CV of the candidates and send them all to the University of Foro Italico which, together with Carolyn Smith and her staff, draw up the ranking
For the purpose of the evaluation of the dancers, candidates will have to send also a short video (1 min). In the video the candidate will have to perform dance single and in pairs.

## Slide 6
Train the Trainers Course:
Course schedule
Friday 8 June
16:00 – 20:00 Dance (theory and practice)
Saturday 9 June
09:00 – 13:00 Theory (theory and practice)
  (PA and health; Breast cancer and PA; Dance Movement Therapy for breast cancer survivors; functional evaluation)
14:30 – 18:30 Dance (theory and practice)
Sunday 10 June
09:00 – 13:00 Dance (with final evaluation)

## Slide 7
Train the Trainers Course:
Replication of the course in the different countries
The training course as organised in Rome will be replicated in each participating country during the project course
The programme and the contents will be adapted by the partners to their contexts and needs but the general structure of the course will be maintained
Once completed the training path for the professionals in each country a pilot action with women affected by breast cancer will start

## Slide 8
Train the Trainers Course:
Replication of the course in the different countries
We have chosen the Train the trainers approach due to its numerous benefits for participants:
instead of relying on one individual to go through a lengthy training process, we can build a team of instructors and enablers so national training initiatives can benefit of first hand perspective.
At the same time, we give our enablers tools concerning not only what to teach, but how to teach so to continue, ideally endless, the training cascade effect.
Finally, this approach guarantees the sustainability of the action because materials produced for 1 course can be used, adapted and replicated in a cascade effect without further costs.